## Sheet1
General Project Information
|  | Project Name | FCI Learining System
|  | sprint time | 1 week
|  | scrum manger | mohamed galal
|  | Stakeholders | any one want E- learning
|  | Expected Start Date | 2018-03-01
|  | Expected Completion Date | 2018-04-13
|  | product owner | E-learing company
|  | Budget | 150$
|  | Risks | low
Story
Planning | Name |  |  | Priority | Status | Responsible | Start | End | Days
Sprint 1 | Home page | as a :admin I want:add features to website so that: make servcise easy | as a :user I want:enter to website so that: know website body | High | In Progress |  | 2018-03-01 | 2018-03-08 | 6
Feature 1 | home | as a :admin I want:enter to website so that: add another thing | as a :user I want:enter to search field so that: search about courses | High | Complete | amr | 2018-03-01 | 2018-03-04 | 3
Feature 2 | search |  |  | Medium | In Progress | mohamed gaber | 2018-03-05 | 2018-03-08 | 3
Sprint 2 | Courses | as a :admin I want:enter to website so that: check the courses | as a :user I want:enter to website so that: choose course | High | Not Started |  | 2018-03-09 | 2018-03-15 | 6
Feature 4 | choose course | as a :admin I want:enter to page so that: add instructors | as a :user I want:enter to page so that:choose instructor | High | Not Started | yasser | 2018-03-09 | 2018-03-12 | 3
Feature 5 | instructor |  |  | Medium | Not Started | abdallah | 2018-03-12 | 2018-03-15 | 3
Sprint 3 | Entering | as a :admin I want:enter to website so that: add another features | as a :user I want:enter to website so that: watch the courses | Medium | Not Started |  | 2018-03-16 | 2018-03-23 | 6
Feature 7 | login | as a :admin I want:enter to data so that: check the data is true | as a :user I want:enter to website so that: watch the courses | Medium | Not Started | yahia | 2018-03-16 | 2018-03-19 | 3
Feature 8 | signup |  |  | Medium | Not Started | yahia | 2018-03-19 | 2018-03-22 | 3
Sprint 4 | Help | as a :admin I want:reply to user so that: help them | as a :user I want:enter to page so that:ask for help | Medium | Not Started |  | 2018-03-23 | 2018-03-29 | 6
Feature 10 | support | as a :admin I want:see data so that: get in touch with users | as a :user I want:enter data so that: contact with admin | Medium | Not Started | mohamed galal | 2018-03-23 | 2018-03-26 | 3
Feature 11 | ContactUs |  |  | Low | Not Started | mohamed gaber | 2018-03-26 | 2018-03-29 | 3
Sprint 5 | Additional | as a :admin I want:enter to bought courses so that: know our profit | as a :user I want:enter to page so that: buy courses | Low | Not Started |  | 2018-03-30 | 2018-04-05 | 6
Feature 13 | buy courses | as a :admin I want:close my e-mail so that: no more things to do | as a :user I want:close my e-mail so that: I watched the course | Low | Not Started | abdallah | 2018-03-30 | 2018-04-01 | 3
Feature 14 | logout |  |  | Low | Not Started | amr | 2018-04-02 | 2018-04-05 | 3
Sprint 6 | Opinion | as a :admin I want:enter data about us so that: user know us | as a :user I want:enter to page so that:know about admins | Low | Not Started |  | 2018-04-06 | 2018-04-13 | 6
Feature 16 | Aboutus | as a :admin I want:enter to database so that: grade of our page | as a :user I want:enter tofeedback so that: give my opinion | Low | Not Started | yasser | 2018-04-06 | 2018-04-09 | 3
Feature 17 | feedback |  |  | Low | Not Started | mohamed galal | 2018-04-10 | 2018-04-13 | 3

## Sheet2
This sheet is to enable the drop-down lists
| High | Complete
| Medium | In Progress
| Low | Not Started